## Test Matrix
# | Module | Feature | Spec | Surface | Design tested | Logic tested | Tenancy tested | Plan gate tested | Test cases | Verified by | Result | Defects | Notes
1 | Billing | Plan activation (subscribe, all tiers) | 15 | Admin | Manual | Yes | Yes | Yes | A-01,A-02 | test-billing-mock.ts | PASS |  | Real test charges on a dev store still pending-manual (needs npm run deploy for the webhook).
2 | Billing | Monthly vs annual interval | 15 | Admin | Manual | Yes | N/A | N/A | A-02,A-03 | test-billing-mock.ts | PASS | D-15 | ANNUAL carries no usage line (Shopify rejects it), so yearly hard-caps at quota.
3 | Billing | Upgrade / downgrade / cancel | 15 | Admin | Manual | Yes | Yes | N/A | A-04,A-05,A-06,A-07 | test-billing-mock.ts | PASS |  | Cancel failure is fail-safe: the Shop row is left untouched.
4 | Billing | Trial handling | 15 | Server | N/A | Yes | N/A | N/A | A-08 | test-billing-mock.ts | PASS | D-08
5 | Billing | Callback verification & idempotency | 15 | Server | N/A | Yes | Yes | N/A | A-09,A-10,A-11,A-12 | test-billing-mock.ts | PASS |  | Plan derived from the verified subscription name, never from ?plan= (anti-escalation).
6 | Billing | app_subscriptions/update webhook | 15 | Server | N/A | Yes | Yes | N/A | A-13,A-14,A-15,A-16 | test-billing-mock.ts | PASS | D-09 | Stale/out-of-order guard verified; FROZEN/PENDING handling added.
7 | Billing | Usage metering & overage | 15 | Server | N/A | Yes | Yes | Yes | A-17,A-18 | test-billing-mock.ts | PASS |  | 30-min session rule; isTest never meters.
8 | Billing | Billing restricted to admin surface | 15/18 | Web | N/A | Yes | N/A | N/A | A-19 | auth-sessions.test.ts | PASS |  | billing_manage is admin-only for every role.
9 | Plans | Matrix matches published pricing | 15 | Server | N/A | Yes | N/A | Yes | B-01 | platform-check.ts | PASS | D-16 | Reconciled 2026-08-21: manual_qas, policy_pages, crawl_pages, team_seats corrected.
10 | Plans | Operator edits propagate to all shops | 19 | Platform | Manual | Yes | Yes | Yes | B-02,B-03 | platform-check.ts | PASS |  | In-process immediately; other processes within the 30s REFRESH_TTL_MS.
11 | Plans | Enforcement switch (open/enforced) | 19 | Platform | Manual | Yes | N/A | Yes | B-05 | platform-check.ts, plan-gates.test.ts | PASS |  | Default flipped to 'enforced' 2026-08-21.
12 | Plans | Quota gates bite (11 dimensions) | 15 | Server | N/A | Yes | Yes | Yes | B-10 | plan-gates.test.ts | PASS
13 | Plans | Feature gates bite (13 features) | 15 | Server | N/A | Yes | Yes | Yes | B-11 | plan-gates.test.ts | PASS
14 | Plans | Downgrade keeps over-quota data | 15 | Server | N/A | Yes | N/A | Yes | B-12 | plan-gates.test.ts | PASS |  | Data retained, new creates blocked. No deletions.
15 | Plans | Never-gate list (inbox/handover/GDPR/Test AI) | 15 | Server | N/A | Yes | N/A | Yes | B-13 | plan-gates.test.ts | PASS |  | No gate identifier exists for these, so no operator edit can disable them.
16 | Plans | New seams: active_campaigns, analytics_range_days | 15 | Server | N/A | Yes | Yes | Yes | B-15 | plan-gates.test.ts | PASS |  | Built 2026-08-21 from the spreadsheet.
17 | Plans | New seams: survey, push, custom recs, multi-language | 15 | Server | N/A | Yes | Yes | Yes | B-15 | plan-gates.test.ts | PASS |  | multi_language was found ungated during planning and added.
18 | Plans | Corrupt override row handling | 19 | Platform | N/A | Yes | N/A | N/A | B-07 | platform-check.ts | PASS | D-12
19 | Promo codes | Code normalization & validation | 15 | Platform/Admin | Manual | Yes | N/A | N/A | C-10,C-18 | promo-codes.test.ts | PASS | D-02,D-18 | Regex bug fixed; percent values >2dp now rejected.
20 | Promo codes | Redemption lifecycle (reserve/confirm/release) | 15 | Server | N/A | Yes | Yes | N/A | C-01,C-13,C-14 | promo-codes.test.ts | PASS | D-04,D-14 | Confirm now also runs from the subscription webhook; pending rows GC'd after 24h.
21 | Promo codes | maxRedemptions atomicity | 15 | Server | N/A | Yes | Yes | N/A | C-05,C-06 | promo-codes.test.ts | PASS | D-06 | Unique constraint + advisory lock; 6-way race yields exactly 1 winner.
22 | Promo codes | Scope rules (plan/interval/expiry/value) | 15 | Server | N/A | Yes | N/A | N/A | C-03,C-04,C-07,C-08 | promo-codes.test.ts | PASS | D-17 | 'Discount too large' copy no longer misreports as a scope problem.
23 | Promo codes | Promo survives a plan change | 15 | Server | N/A | Yes | Yes | N/A | C-12 | promo-codes.test.ts | PASS | D-07 | Redemption follows the shop, not the subscription id.
24 | Promo codes | Enumeration throttle | 15 | Admin | N/A | Yes | Yes | N/A | C-17 | promo-codes.test.ts | PASS | D-19 | 10/min per shop, spent only on failures.
25 | Promo codes | Operator console (create/toggle/delete) | 19 | Platform | Manual | Yes | N/A | N/A | C-15 | promo-codes.test.ts | PASS |  | Delete blocked for ever-redeemed codes.
26 | AI pipeline | Golden set (grounded routing) | 03 | Server | N/A | Yes | Yes | N/A | D-01,D-10 | eval-golden.ts | PASS
27 | AI pipeline | Model family portability (gpt-4 vs reasoning) | 03 | Server | N/A | Yes | N/A | N/A | D-02,D-03,D-04 | model-compat-check.ts, model-portability.test.ts | PASS |  | gpt-4 family params byte-identical; switching models needs no code change.
28 | AI pipeline | Platform AI overrides don't de-tune the router | 19 | Server | N/A | Yes | N/A | N/A | D-05,D-06 | model-portability.test.ts | PASS | D-03
29 | AI pipeline | Embedding model change safety | 01/03 | Server | N/A | Yes | N/A | N/A | D-08 | model-portability.test.ts | PASS | D-05 | Fails closed at toSqlVector; re-embed path added for all four vector columns.
30 | AI pipeline | Chat rate-limit backoff | 03 | Server | N/A | Yes | N/A | N/A | D-09 | model-portability.test.ts | PASS | D-13
31 | AI pipeline | Guardrails / banned topics | 03/08 | Server | N/A | Yes | Yes | N/A | D-12 | eval-golden.ts | PASS |  | One documented router flake on an edge phrasing — see PROGRESS decisions log.
32 | AI pipeline | Test AI console never meters | 08 | Admin | Manual | Yes | Yes | N/A | D-13 | test-analytics.ts | PASS
33 | AI pipeline | Vector search stack (hybrid/keyword/curated) | 01 | Server | N/A | Yes | Yes | N/A | D-11 | smoke-vector.ts, perf-queries.test.ts | PARTIAL | D-41 | Curated match confirmed using HNSW. OPEN: a LEFT JOIN in knowledge search structurally prevents HNSW from being chosen.
34 | Knowledge | Five source types + retrievability | 04 | Admin | Manual | Yes | Yes | Yes | E-01,E-02,E-06 | test-ingest.ts | PASS
35 | Knowledge | SSRF hardening on URL crawl | 04 | Server | N/A | Yes | N/A | N/A | E-03 | test-ingest.ts | PASS
36 | Knowledge | Ingestion quotas per tier | 04/15 | Server | N/A | Yes | Yes | Yes | E-04 | plan-gates.test.ts | PASS
37 | Knowledge | Unsupported file types & failed ingest | 04 | Admin | Manual | Yes | N/A | N/A | E-05,E-08 | test-ingest.ts | PASS |  | PDF/DOCX parsing deferred by design; errors cleanly.
38 | Catalog sync | Products/collections/discounts mirror | 02 | Server | N/A | Yes | Yes | Yes | Q-02 | smoke-vector.ts, install-lifecycle.test.ts | PASS |  | Daily reconcile prunes deleted items.
39 | Catalog sync | Webhooks enqueue-only | 02 | Server | N/A | Yes | Yes | N/A | J-05 | install-lifecycle.test.ts | PASS |  | Embedding work never happens inside the request.
40 | Widget | Launcher variants & theming | 05/06 | Storefront | Manual | Yes | N/A | N/A | F-01 | manual | PENDING-MANUAL |  | Needs a storefront browser pass.
41 | Widget | SSE streaming + truncation/stall recovery | 05 | Storefront | Manual | Yes | N/A | N/A | F-02,F-03,F-04 | code-verified | PASS |  | Watchdog + truncation guard added in the previous QA pass.
42 | Widget | Product cards + one-click add to cart | 05 | Storefront | Manual | Yes | N/A | N/A | F-05 | manual | PENDING-MANUAL |  | Requires a real theme cart drawer.
43 | Widget | Pre-chat form | 05 | Storefront | Manual | Yes | Yes | N/A | F-06,I-09 | code-verified | PASS |  | Cross-session contact hijack fixed previously (sessionId binding).
44 | Widget | FAQ screen + server-side search | 05 | Storefront | Manual | Yes | Yes | N/A | F-07 | code-verified | PASS
45 | Widget | Order tracking (3 modes) | 05/16 | Storefront | Manual | Yes | Yes | N/A | F-08,F-09 | code-verified | PASS |  | Throttled 8/min; never echoes the order's own PII.
46 | Widget | Post-chat survey | 05/16 | Storefront | Manual | Yes | Yes | Yes | F-10 | plan-gates.test.ts | PASS |  | Now gated Basic+ server-side at proxy.survey.
47 | Widget | Thread persistence & restore | 05 | Storefront | Manual | Yes | Yes | N/A | F-11 | code-verified | PASS
48 | Widget | Blocked visitor | 10 | Storefront | Manual | Yes | Yes | N/A | F-12 | handover.test.ts | PASS
49 | Widget | Proactive campaigns + CTA safety | 12 | Storefront | Manual | Yes | Yes | Yes | F-13,F-14,Q-09 | test-campaign-triggers.ts, test-campaign-metrics.ts | PASS |  | Revenue recomputed server-side; client beacon ignored.
50 | Widget | Performance budget (<=30KB gz) | 05 | Storefront | N/A | Yes | N/A | N/A | F-16 | check-widget-size.ts | PASS
51 | Widget | Branding removal gate | 06/15 | Storefront | Manual | Yes | Yes | Yes | F-17 | plan-gates.test.ts | PASS |  | Decided server-side; the client cannot spoof it.
52 | Widget | Renders nothing for an uninstalled shop | 05 | Storefront | N/A | Yes | Yes | N/A | F-15,N-07 | install-lifecycle.test.ts | PASS
53 | Handover | All five triggers | 10 | Server | N/A | Yes | Yes | N/A | G-01..G-05 | handover.test.ts | PASS | D-20 | repeated_question uses exact text, not embeddings, contrary to spec 10.
54 | Handover | Three destinations x online/offline | 10 | Server | N/A | Yes | Yes | N/A | G-06..G-09 | handover.test.ts | PASS | D-10 | contact_methods chips added to the chat thread.
55 | Handover | AI dormancy (aiWhileWaiting) | 10 | Server | N/A | Yes | N/A | N/A | G-10 | handover.test.ts | PASS
56 | Handover | Two-way delivery + Seen | 10 | Admin/Web | Manual | Yes | Yes | N/A | G-11,G-12,G-13 | handover.test.ts | PASS |  | Merchant replies reach the shopper outside human-mode too (fixed previously).
57 | Handover | Resolve / reopen / auto-resolve | 10 | Admin/Web | Manual | Yes | Yes | N/A | G-14,G-15,G-16 | handover.test.ts | PASS | D-11 | Reopen now returns the thread to AI mode.
58 | Handover | Merchant notification (email + push) | 10/18 | Server | N/A | Yes | Yes | Yes | G-17,G-18 | handover.test.ts | PASS |  | Owner row bootstrapped lazily; no transcript in email (PII minimisation).
59 | Handover | Conversation ownership binding | 10 | Server | N/A | Yes | Yes | N/A | G-19 | handover.test.ts | PASS |  | Every widget lookup binds conversationId AND sessionId.
60 | Availability | Working hours / breaks / holidays | 16 | Server | Manual | Yes | Yes | N/A | H-02,H-05,H-06 | availability.test.ts | PASS | D-21 | Holiday date-format validation added.
61 | Availability | Timezone + overnight + DST | 16 | Server | N/A | Yes | Yes | N/A | H-03,H-04,H-08 | availability.test.ts | PASS |  | Evaluated in the shop's timezone.
62 | Availability | onlineStatusMode (all three) | 16 | Server | N/A | Yes | N/A | N/A | H-07 | availability.test.ts | PASS | D-01 | agentOnline was never wired, leaving two of three modes dead. Fixed.
63 | Availability | Offline widget copy & status freshness | 16 | Storefront | Manual | Yes | N/A | N/A | H-09,H-10 | availability.test.ts | PASS | D-22 | Cache could make the status contradict the handover branch.
64 | Inbox | Filters, counts, actions | 10 | Admin/Web | Manual | Yes | Yes | Yes | I-01,I-04,I-05 | handover.test.ts, perf-queries.test.ts | PARTIAL | D-39 | Actions and counts correct. OPEN: filters + unread badge are computed in JS over a 300-row window, so above 300 conversations they only reflect the newest 300.
65 | Inbox | Unread badge excludes test chats | 10 | Admin/Web | N/A | Yes | Yes | N/A | I-02 | test-analytics.ts | PASS |  | Fixed in the previous QA pass.
66 | Inbox | SSE live feed + fallback | 18 | Admin/Web | Manual | Yes | Yes | N/A | I-03 | routing.test.ts | PASS
67 | Contacts | List, stats, classification | 11 | Admin/Web | Manual | Yes | Yes | N/A | I-06 | code-verified | PASS
68 | Contacts | CSV export (injection-safe, gated) | 11/15 | Admin/Web | N/A | Yes | Yes | Yes | I-07 | plan-gates.test.ts | PASS |  | Formula-injection guard added previously.
69 | Contacts | Duplicate email handling | 11 | Admin/Web | N/A | Yes | Yes | N/A | I-08 | code-verified | PASS |  | Case-insensitive.
70 | Routing | Embedded admin routes (21) | — | Admin | Manual | Yes | Yes | N/A | J-01,J-06,J-11 | routing.test.ts | PASS
71 | Routing | Web routes (8) | 18 | Web | Manual | Yes | Yes | N/A | J-02,J-08 | routing.test.ts | PASS | D-35,D-36 | Logout-CSRF and forgot-CSRF guards added. HTTP assertions need a re-run after the dev server is restarted.
72 | Routing | Platform routes (12) | 19 | Platform | Manual | Yes | Yes | N/A | J-03,J-08 | routing.test.ts | PASS | D-37,D-29 | Deep-link query preserved on auth bounce; console no longer framable via a shop param.
73 | Routing | App proxy routes (11) | 05 | Storefront | N/A | Yes | Yes | N/A | J-04 | routing.test.ts | PASS |  | Shop identity only from the verified proxy signature.
74 | Routing | Webhook routes (8) | 17 | Server | N/A | Yes | Yes | N/A | J-05 | install-lifecycle.test.ts | PASS |  | Invalid HMAC rejected before handler code.
75 | Routing | Nav integrity & role filtering | 18 | Admin/Web | Manual | Yes | N/A | N/A | J-09 | routing.test.ts | PASS
76 | Routing | No shop-domain login form (req 2.3.1) | 17 | Public | N/A | Yes | N/A | N/A | J-10 | compliance | PASS
77 | Auth | Shopify session storage lifecycle | 01 | Server | N/A | Yes | Yes | N/A | K-01 | auth-sessions.test.ts | PASS
78 | Auth | TeamSession / PlatformSession TTL & cleanup | 18/19 | Web/Platform | N/A | Yes | Yes | N/A | K-02,K-03,K-04 | auth-sessions.test.ts | PASS | D-23 | Expired-session pruning added.
79 | Auth | Role authorization matrix | 18 | Web | N/A | Yes | Yes | N/A | K-05,K-06 | auth-sessions.test.ts | PASS |  | Verified by direct URL, not just nav hiding.
80 | Auth | Login hardening (enumeration, lockout, CSRF) | 18/19 | Web/Platform | N/A | Yes | N/A | N/A | K-07,K-08,K-16 | auth-sessions.test.ts, platform-lockout-probe.ts | PASS
81 | Auth | Token single-use (invite/reset/handoff) | 18 | Web | N/A | Yes | Yes | N/A | K-10,K-11 | auth-sessions.test.ts | PASS |  | Replay refused.
82 | Auth | Open-redirect protection | 18 | Web | N/A | Yes | N/A | N/A | K-09 | auth-sessions.test.ts | PASS
83 | Auth | Cookie flags & iframe isolation | 18 | Web/Platform | N/A | Yes | Yes | N/A | K-13,K-14,K-15 | auth-sessions.test.ts | PASS |  | HttpOnly/Secure/SameSite=Lax verified from real response headers.
84 | Web app | Team login & multi-shop picker | 18 | Web | Manual | Yes | Yes | N/A | K-05,K-07 | auth-sessions.test.ts | PASS
85 | Web app | Invites, password reset, seats quota | 18/15 | Web | Manual | Yes | Yes | Yes | K-10,B-10 | auth-sessions.test.ts, plan-gates.test.ts | PASS |  | team_seats quota corrected to 1/2/5/10.
86 | Web app | Admin -> web handoff token | 18 | Admin/Web | Manual | Yes | Yes | N/A | K-10 | auth-sessions.test.ts | PASS |  | 2-minute single-use.
87 | Web app | Browser push notifications | 18/15 | Web | Manual | Yes | Yes | Yes | B-15,G-17 | plan-gates.test.ts | PASS |  | Now gated Basic+; unsubscribe stays open after a downgrade.
88 | Web app | Account page & sign-out everywhere | 18 | Web | Manual | Yes | Yes | N/A | K-11,K-12 | auth-sessions.test.ts | PASS
89 | Platform | Operator auth & admin management | 19 | Platform | Manual | Yes | N/A | N/A | P-01,P-03 | platform-lockout-probe.ts | PASS |  | Cannot remove yourself or the last admin.
90 | Platform | Cross-tenant overview & usage reporting | 19 | Platform | Manual | Yes | Yes | N/A | P-02,P-06 | usage-check.ts | PASS | D-24 | Streamed calls counted exactly once.
91 | Platform | Runtime settings (secrets, providers, flags) | 19 | Platform | Manual | Yes | N/A | N/A | P-05 | platform-settings-check.ts | PASS |  | Secrets AES-GCM encrypted at rest; never sent to the browser.
92 | Platform | AI model settings | 19 | Platform | Manual | Yes | N/A | N/A | P-04,D-07 | model-portability.test.ts | PASS
93 | Logging | Levels, attribution, redaction | 21 | Server | N/A | Yes | Yes | N/A | P-07,P-08,P-09 | logs-check.ts, logs.test.ts | PASS |  | warn/error only by design.
94 | Logging | Rate cap & retention | 21 | Server | N/A | Yes | Yes | N/A | P-10,P-11 | logs-check.ts | PASS | D-25 | Cap is per process — documented multi-instance implication.
95 | Logging | Operator log console | 21 | Platform | Manual | Yes | Yes | N/A | P-12 | logs.test.ts | PASS
96 | Database | Query efficiency at volume | 01 | Server | N/A | Yes | Yes | N/A | L-01..L-05,L-07 | perf-queries.test.ts | PASS |  | Measured at ~20k conversations / 200k messages.
97 | Database | N+1 elimination | 01 | Server | N/A | Yes | N/A | N/A | L-06 | perf-queries.test.ts | PASS | D-26
98 | Database | Migrations & schema integrity | 01 | Server | N/A | Yes | N/A | N/A | — | prisma migrate status, smoke-vector.ts | PASS |  | Hand-written HNSW/GIN indexes preserved by scrub-migration.
99 | Caching | TTL + invalidation across five caches | 01/19 | Server | N/A | Yes | Yes | N/A | M-01..M-06 | cache.test.ts | PASS
100 | Install | Fresh install default state | 01/02 | Server | N/A | Yes | Yes | N/A | N-01,N-02 | install-lifecycle.test.ts | PASS
101 | Install | Reinstall & uninstall | 17 | Server | N/A | Yes | Yes | N/A | N-03,N-04,N-05 | install-lifecycle.test.ts | PASS |  | No dead subscription resumed inside the grace window.
102 | Compliance | Three mandatory GDPR webhooks | 17 | Server | N/A | Yes | Yes | N/A | O-01..O-04 | verify-compliance.ts | PASS
103 | Compliance | Retention & full tenant purge | 17 | Server | N/A | Yes | Yes | N/A | O-05,N-06 | verify-compliance.ts | PASS |  | Zero-row assertion across every table.
104 | Compliance | App Store review checklist | 17 | — | Manual | Yes | Yes | N/A | O-07..O-11 | APP-STORE-REVIEW.md | PASS |  | Re-executed 2026-08-21.
105 | Compliance | Privacy policy & listing copy | 17 | — | Manual | N/A | N/A | N/A | O-12 | manual | PENDING-MANUAL |  | Must name OpenAI + Resend as processors before submission.
106 | Compliance | Lighthouse on a storefront page | 05 | Storefront | Manual | N/A | N/A | N/A | O-10 | manual | PENDING-MANUAL
107 | Dashboard | KPIs, onboarding checklist, live feed | 13 | Admin/Web | Manual | Yes | Yes | N/A | Q-01 | test-analytics.ts | PASS
108 | Chatbox | Settings tabs + live preview parity | 06 | Admin/Web | Manual | Yes | Yes | Yes | Q-03 | manual | PENDING-MANUAL |  | Preview parity is a visual judgement.
109 | AI training | Five training tabs + metafield opt-in | 07 | Admin/Web | Manual | Yes | Yes | Yes | Q-04 | plan-gates.test.ts | PASS
110 | AI instructions | Persona, guardrails, recs, handover config | 08 | Admin/Web | Manual | Yes | Yes | Yes | Q-05 | plan-gates.test.ts, handover.test.ts | PASS
111 | Curated answers | CRUD, quota, embedding, sanitisation | 09 | Admin/Web | Manual | Yes | Yes | Yes | Q-06,D-11 | plan-gates.test.ts, seed-curated.ts | PASS |  | 20 answers seeded incl. near-miss pairs for threshold testing.
112 | Analytics | Reports, funnel, CSAT, top questions | 14 | Admin/Web | Manual | Yes | Yes | Yes | Q-07 | test-analytics.ts | PASS | D-40 | Test chats excluded; rollup idempotent. OPEN: a cold 12-month range issues 2,191 statements (3.8s) — needs a set-based rollupRange.
113 | Analytics | History range gated by plan | 14/15 | Server | N/A | Yes | Yes | Yes | B-15 | plan-gates.test.ts | PASS |  | New analytics_range_days quota: 7/30/90/365.
114 | Settings | General / chatbox / privacy tabs | 16 | Admin/Web | Manual | Yes | Yes | Yes | Q-08 | manual | PENDING-MANUAL |  | Server-side save paths covered; visual pass outstanding.
115 | Settings | FAQ CSV import | 16 | Admin/Web | N/A | Yes | Yes | Yes | Q-12 | code-verified | PASS |  | Header detection + dedupe fixed in the previous pass.
116 | Campaigns | Dashboard, templates, editor, metrics | 12 | Admin/Web | Manual | Yes | Yes | Yes | Q-09 | test-campaign-metrics.ts | PASS
117 | UI | Unsaved-changes guard (both surfaces) | — | Admin/Web | Manual | Yes | N/A | N/A | Q-11 | code-verified | PASS |  | useBlocker + beforeunload added previously.
118 | UI | Mobile responsiveness (~390px) | 20 | Admin/Web | Manual | N/A | N/A | N/A | Q-10 | manual | PENDING-MANUAL |  | Single 768px breakpoint; desktop must stay pixel-identical.

## Defects
ID | Severity | Area | File | Summary | Status | Verified by
D-01 | High | Availability | app/lib/settings/availability.server.ts | agentOnline was never passed by any caller, so onlineStatusMode 'agent_during_hours' resolved offline forever and 'working_hours_or_agent' degraded to plain working_hours — two of three modes dead. Agent presence is now derived from inbox activity. | Fixed | availability.test.ts (96)
D-02 | High | Promo codes | app/lib/billing/promo-shared.ts | normalizePromoCode used a literal-s regex instead of a whitespace one; toUpperCase() runs first so it could never match. Whitespace was never stripped and 'SAVE 20' failed with a generic format error. | Fixed | promo-codes.test.ts (89)
D-03 | High | AI pipeline | app/lib/llm/openai.server.ts | Platform temperature/maxTokens overrides won over every per-call value including the router's strict-JSON tuning. Reproduced live: the router returned truncated JSON and every shopper turn on every tenant silently fell back to the chat lane. Params are now pinned by purpose. | Fixed | model-portability.test.ts (88)
D-04 | High | Promo codes | app/lib/billing/promo-codes.server.ts | Redemption was confirmed only from the billing callback, so approving then closing the tab left the row pending forever: discount live on Shopify but never counted toward maxRedemptions and never blocked reuse. Now also confirmed from the subscription webhook. | Fixed | promo-codes.test.ts
D-05 | High | Embeddings | scripts/reembed-products.ts | Changing the embedding model had no migration path: the model was not part of contentHash so the script reported '0 to re-embed', and three of four vector columns had no re-embed path at all. A marker row now records which model built the vectors. | Fixed | model-portability.test.ts
D-32 | High | Compliance | app/routes/webhooks.compliance.tsx | shop/redact stamped uninstalledAt but left plan/subscriptionId intact. If app/uninstalled was missed, a reinstall inside the 7-day window resurrected a paid plan against a subscription Shopify had already cancelled — a free paid tier, indefinitely. | Fixed | install-lifecycle.test.ts (104)
D-35 | High | Auth | app/routes/web.logout.tsx | web.logout had no sameOrigin guard (platform.logout did), so a cross-site auto-submitting POST form was a working logout CSRF. | Fixed | auth-sessions.test.ts
D-36 | High | Auth | app/routes/web.forgot.tsx | web.forgot had no sameOrigin guard, so any page could mint password-reset links and fire reset emails at an arbitrary address. | Fixed | auth-sessions.test.ts
D-39 | High | Inbox | app/lib/inbox/inbox.server.ts | listConversations fetches take:300 and every filter (open/resolved/unassigned/handover/starred/blocked) plus the unread badge is applied in JavaScript over that window. Above 300 conversations the filters show only what is in the newest 300 and the badge undercounts — a correctness bug, not just perf. Server-side equivalents measured at 0.1-0.9ms. | Open | perf-queries.test.ts
D-06 | Medium | Promo codes | app/lib/billing/promo-codes.server.ts | maxRedemptions was not atomic — count() at validate time, create much later, no unique constraint. A 6-way race on a 1-use code produced 4 winners; now exactly 1 (unique index + advisory lock + reservation before subscribe). | Fixed | promo-codes.test.ts
D-07 | Medium | Promo codes | app/lib/billing/promo-codes.server.ts | A promo silently died on a plan change: the new subscription id plus the one-per-shop rule meant a 'forever' discount evaporated on upgrade. Redemptions now follow the shop and are carried into the new subscription. | Fixed | promo-codes.test.ts
D-08 | Medium | Billing | app/lib/jobs/handlers.server.ts | Nothing moved planStatus from 'trial' to 'active' when trialEndsAt passed unless a webhook happened to arrive. A nightly transitionExpiredTrials() sweep now does it, and never resurrects a shop with no subscription. | Fixed | test-billing-mock.ts
D-09 | Medium | Billing | app/routes/webhooks.app-subscriptions.tsx | FROZEN and PENDING statuses fell into the ignore branch, so an unpaid frozen subscription left the merchant on the paid tier indefinitely. FROZEN now suspends the entitlement while keeping subscriptionId so an unfreeze restores it. | Fixed | subscription-webhook.test.ts (12)
D-10 | Medium | Handover | extensions/chat-widget/assets/chat-widget.js | handleHandover had no contact_methods branch, so spec 10's contact chips never appeared in the chat thread (home screen only). | Fixed | handover.test.ts (197)
D-12 | Medium | Plans | app/lib/platform/platform-settings.server.ts | getStoredPlanConfig() swallowed parse failures into an empty object, so one corrupt row plus one operator edit silently discarded every other plan's overrides and the enforcement mode. Now logged loudly and the unparseable value is archived for recovery. | Fixed | platform-check.ts
D-13 | Medium | AI pipeline | app/lib/llm/openai.server.ts | withBackoff covered embeddings only, so a 429 on chat surfaced straight to the shopper. Now wraps chat() and the chatStream() handshake. | Fixed | model-portability.test.ts
D-14 | Medium | Promo codes | app/lib/billing/promo-codes.server.ts | Abandoned pending redemptions were never garbage-collected, and a downgrade left rows in place so a shop could never reuse its own code. Pending rows now expire after 24h and cancel/downgrade/uninstall release the slot. | Fixed | promo-codes.test.ts
D-15 | Medium | Billing | app/routes/app.plan-usage.tsx | The plan FAQ read the tier's headline overage rate, but Shopify rejects usage line items on ANNUAL subscriptions so a yearly subscriber hard-caps at quota. The copy promised overage billing they can never receive. Now driven by the same overageBillable() predicate the meter uses. | Fixed | test-billing-mock.ts
D-16 | Medium | Plans | app/lib/billing/plans.server.ts | The code matrix diverged from plan-allocation.xlsx (manual_qas, policy_pages, crawl_pages, team_seats) and six gates/quotas in the sheet did not exist in code at all. Reconciled; enforcement flipped from open to enforced. | Fixed | platform-check.ts, plan-gates.test.ts (27)
D-22 | Medium | Availability | app/lib/widget/config.server.ts | Widget config cached 5 min server-side plus 5 min in sessionStorage, so the online/offline badge could contradict the live handover branch for ~10 minutes. The payload now carries a computed ttl to the next status change; worst case ~60s. | Fixed | availability.test.ts
D-29 | Medium | Security | app/entry.server.tsx | addDocumentResponseHeaders sets frame-ancestors for the shop whenever a shop param is present and ran before the deny block, so appending one made the cross-tenant operator console framable. /platform is now in the deny branch; nosniff added globally; /app documents get no-store. | Fixed | routing.test.ts (source)
D-30 | Medium | Compliance | app/routes/auth.login/ | The template's shop-domain login form was still shipped and reachable, violating App Store requirement 2.3.1 (never ask a merchant to type their myshopify domain). Route deleted, login export removed, redirect_urls cleaned; the path now redirects to the marketing page instead of 500ing. | Fixed | compliance re-audit
D-31 | Medium | Billing | app/lib/billing/shopify-billing.server.ts | billingTestMode swapped in a mock provider that persists a paid plan against a fabricated subscription gid with no Shopify charge, and its verified name is rebuilt from the client's plan param — making the anti-escalation check self-fulfilling. Now hard-disabled when NODE_ENV is production. | Fixed | code-verified
D-33 | Medium | Compliance | app/lib/jobs/handlers.server.ts | PromoRedemption is shop-scoped but survived cleanupShop — an orphan row after GDPR erasure that also held a maxRedemptions slot forever. | Fixed | verify-compliance.ts (34 tables)
D-34 | Medium | Install | app/routes/webhooks.app.scopes_update.tsx | Updated only one of a shop's session rows and threw P2025 leading to a 500 and infinite Shopify retries if the row was deleted by a racing uninstall. Rewritten to updateMany keyed by shop. | Fixed | install-lifecycle.test.ts
D-37 | Medium | Routing | app/lib/platform/platform-auth.server.ts | Platform deep links lost their query string on the auth bounce (a range param on the usage page was dropped). | Fixed | routing.test.ts
D-38 | Medium | Caching | app/routes/app._index.tsx, app/lib/jobs/handlers.server.ts | Two writers never invalidated the 60s shop-config cache: the dashboard identity backfill, and GDPR cleanupShop — so the pipeline could serve a redacted shop's deleted persona and guardrails for up to a minute after erasure. | Fixed | cache.test.ts (31)
D-40 | Medium | Analytics | app/lib/analytics/reports.server.ts | A 12-month analytics range with no cached rollup issues 2,191 statements (365 x rollupDay) = 3.8s wall. Indexes made each query 14-60x faster but round-trip count dominates. Needs a set-based rollupRange(); deliberately not rewritten during a QA pass. | Open | perf-queries.test.ts
D-41 | Medium | Search | app/lib/search/knowledge-search.server.ts | A LEFT JOIN over data_sources sits above the vector ORDER BY, forcing a sort of the whole result set and structurally preventing HNSW from ever being chosen. Filter by dataSourceId instead. Re-verify with real embeddings. | Open | perf-queries.test.ts
D-42 | Medium | Tooling | scripts/scrub-migration.ts | npm run migrate:new scrubs the alphabetically last migration folder. With a future-timestamped migration present it scrubbed the wrong folder, leaving 6 spurious DROP INDEX statements that would have dropped the hand-written HNSW/GIN indexes. | Open | manual
D-11 | Low | Inbox | app/lib/inbox/inbox.server.ts | NOT CONFIRMED as a defect: both paths to resolved already set mode to ai, so a reopened thread was never stuck in human mode. Made explicit anyway so the invariant holds for seeded/imported rows. | No change needed | handover.test.ts
D-17 | Low | Promo codes | app/components/PlanCards.tsx | A fixed discount larger than the plan price showed the full price with no explanation, then failed at subscribe with a misleading 'wrong plan' message. | Fixed | promo-codes.test.ts
D-18 | Low | Promo codes | app/lib/billing/promo-shared.ts | Percent values with more than 2 decimals were silently rounded before being sent to Shopify. | Fixed | promo-codes.test.ts
D-19 | Low | Promo codes | app/lib/billing/promo-codes.server.ts | The validate_code action had no rate limiting, allowing code enumeration by any authenticated merchant. Now a 10/min token bucket spent only on failures. | Fixed | promo-codes.test.ts
D-20 | Low | Handover | app/lib/pipeline/handover.server.ts | repeated_question uses exact normalized-text matching; spec 10 specifies embedding similarity, so paraphrases are not caught. Spec 10's two-thumbs-down trigger is unimplemented. Both are behaviour changes needing a product decision. | Documented | handover.test.ts
D-21 | Low | Availability | app/lib/settings/availability.server.ts | Holiday dates are plain strings in the read schema. Not reachable from the merchant (the save path and the date input both validate), but seeds/imports/direct writes could store a malformed date that silently never matched. The engine now guards the format. | Fixed | availability.test.ts
D-23 | Low | Auth | app/lib/jobs/handlers.server.ts | Expired platform_sessions were never pruned and accumulated forever. team_sessions were already pruned — the 17 rows are live multi-device sessions, 0 expired. | Fixed | auth-sessions.test.ts
D-24 | Low | Tooling | scripts/usage-check.ts | The header claimed it restored llm_usage_daily counters but it only diffed a baseline, so dev-shop counters inflated on every run. Now restores exactly (verified byte-identical round-trip). | Fixed | usage-check.ts
D-25 | Low | Logging | app/lib/log.server.ts | The 50-rows-per-event-per-hour cap is per process, so an N-instance deployment writes up to 50 times N rows/hour/event. A shared counter would need Redis or a DB round-trip in the chat hot path, which the spec forbids. Documented inline. | Documented | logs-check.ts
D-26 | Low | Database | app/lib/contacts/contacts.server.ts, app/lib/dashboard/dashboard.server.ts | N+1: one message lookup per conversation in contactDetail (19 to 10 statements) and in the dashboard live feed on every poll (6 to 3). Seven more remain in background jobs and are reported, not fixed. | Fixed | perf-queries.test.ts (46)
D-27 | Low | Tooling | scripts/set-plan.ts | An unfiltered updateMany repointed every shop on the connected DB, including other scripts' fixture shops mid-run. Now defaults to the dev shop; --all keeps the old behaviour. | Fixed | manual
D-28 | Low | Tooling | scripts/usage-check.ts | Found while fixing D-24: the baseline map was keyed on model and purpose but the table is unique on shop, date, model and purpose — so every day's row collapsed onto one entry and the delta assertions compared today's counters against an arbitrary older day. | Fixed | usage-check.ts
D-43 | Low | Routing | shopify.app.toml | /api/auth was declared in redirect_urls but no route exists for it (dead config from the Remix template). Removed. | Fixed | routing.test.ts

## Summary
ChatConvert — QA summary
Generated 2026-08-21 · pre-submission QA campaign
Result | Features | Share
PASS | 109 | 92%
FAIL | 0 | 0%
PARTIAL | 2 | 2%
PENDING-MANUAL | 7 | 6%
Total | 118 | 100%
Module | Features | Passed | Pending manual
Billing | 8 | 8 | 0
Plans | 10 | 10 | 0
Promo codes | 7 | 7 | 0
AI pipeline | 8 | 7 | 0
Knowledge | 4 | 4 | 0
Catalog sync | 2 | 2 | 0
Widget | 13 | 11 | 2
Handover | 7 | 7 | 0
Availability | 4 | 4 | 0
Inbox | 3 | 2 | 0
Contacts | 3 | 3 | 0
Routing | 7 | 7 | 0
Auth | 7 | 7 | 0
Web app | 5 | 5 | 0
Platform | 4 | 4 | 0
Logging | 3 | 3 | 0
Database | 3 | 3 | 0
Caching | 1 | 1 | 0
Install | 2 | 2 | 0
Compliance | 5 | 3 | 2
Dashboard | 1 | 1 | 0
Chatbox | 1 | 0 | 1
AI training | 1 | 1 | 0
AI instructions | 1 | 1 | 0
Curated answers | 1 | 1 | 0
Analytics | 2 | 2 | 0
Settings | 2 | 1 | 1
Campaigns | 1 | 1 | 0
UI | 2 | 1 | 1
Defect severity | Count | Fixed
High | 9 | 8
Medium | 21 | 18
Low | 13 | 10
Total defects | 43 | 36